## Talent Training Project Plan
Project Delivery Mode | Start Date | End Date | No. OF Hours | Status | Participants
Project Definition | 2015-07-18 | 2015-07-18 | 3 | Complete | Venkat
Project Requirements | 2015-07-25 | 2015-07-25 | 3 | Complete | Team
Project Design
Database Design |  |  | 3 | Complete | Team
Requirement Documnetation |  |  | 3 |  | Team
Project Development/Build | 2015-08-15 | 2015-08-29 | 20 |  | Team
Project Testing | 2015-08-22 | 2015-08-29 | 3 |  | Team
Project Deployment | 2015-08-29 | 2015-08-29 | 2 |  | Team
Project Closure | 2015-08-29 | 2015-08-29 | 2 |  | Team